## Slide 1: Unit-3 Managing Software Project
Prof. Jignasu Mahidhareeya
jignasu.mahidhareeya@darshan.ac.in
+ 91 9890261198
Computer Engineering Darshan Institute of Engineering & Technology
2160701
SOFTWARE ENGINEERING

## Slide 2: Outlines
Software Metrics
  Process, Product and Project Metrics
Software Project Estimations
Software Project Planning (MS Project Tool)
Project Scheduling and Tracking
Risk Analysis and Management
  Risk Identification
  Risk Projection
  Risk Refinement
  Risk Mitigation

## Slide 3: Terminologies
Measure
  It provides a quantitative indication of the extent (range), amount, dimension, capacity or size of some attributes of a product or process.
    Ex., the number of uncovered errors.
Metrics
  Is a quantitative measure of the degree (limit) to which a system, component or process possesses (obtain) a given attribute.
  It relates individual measures in some way.
    Ex., number of errors found per review.

## Slide 4: Terminologies (Cont…)
Indicators
  Is a metric or combination of metrics that provides insight into the software process, project or the product itself.
  It enables the project manager or software engineers to adjust the process, the project or the product to make things better.
    Ex., Product Size (analysis and specification metrics) is an indicator of increased coding, integration and testing effort
Direct Metrics
  Immediately measurable attributes.
    Ex., Line of Code (LOC), Execution Speed, Defects Reported
Indirect Metrics
  Aspects that are not immediately quantifiable.
    Ex., Functionality, Quantity, Reliability

## Slide 5: Terminologies (Cont…)
Faults
  Errors
    Faults found by the practitioners during software development.
  Defects
    Faults found by the customers after release.

## Slide 6: Why Measure Software?
To determine (to define) quality of a product or process.
To predict qualities of a product or process.
To improve quality of a product or process.

## Slide 7: Metric Classification Base
Process
  Specifies activities related to production of software.
  Specifies the abstract set of activities that should be performed to go from user needs to final product.
Project
  Software development work in which a software process is used.
  The actual act of executing the activities for some specific user needs.
Product
  The outcomes of a software project.
  All the outputs that are produced while the activities are being executed.

## Slide 8: 1. Process Metrics
Process Metrics are an invaluable tool for companies to monitor, evaluate and improve their operational performance across the enterprise.
They are used for making strategic decisions.
Process Metrics are collected across all projects and over long periods of time.
Their intent is to provide a set of process indicators that lead to long-term software process improvement.
  Ex., Defect Removal Efficiency (DRE) metric
    Relationship between errors (E) and defects (D)
    The ideal is a DRE of 1:
    DRE = E / ( E + D )

## Slide 9: 1. Process Metrics (Cont…)
We measure the effectiveness of a process by deriving a set of metrics based on outcomes of the process such as,
  Errors uncovered before release of the software
  Defects delivered to and reported by the end users
  Work products delivered
  Human effort expended
  Calendar time expended
  Conformance to the schedule
  Time and effort to complete each generic activity

## Slide 10: 2. Project Metrics
Project metrics enable a software project manager to,
  Assess the status of an ongoing project
  Track potential risks
  Uncover problem areas before their status becomes critical
  Adjust work flow or tasks
  Evaluate the project team’s ability to control quality of software work products
Many of the same metrics are used in both the process and project domain.
Project metrics are used for making tactical (smart) decisions.
They are used to adapt project workflow and technical activities.

## Slide 11: 2. Project Metrics (Cont…)
Project metrics are used to
  Minimize the development schedule by making the adjustments necessary to avoid delays and mitigate (to reduce) potential (probable) problems and risks.
  Assess (evaluates) product quality on an ongoing basis and guides to modify the technical approach to improve quality.

## Slide 12: 3. Product Metrics
Product metrics help software engineers to gain insight into the design and construction of the software they build,
By focusing on specific, measurable attributes of software engineering work products.
Product metrics provide a basis from which analysis, design, coding and testing can be conducted more objectively and assessed more quantitatively.
  Ex., Code Complexity Metric

## Slide 13: Types of Measures
Two categories of software measurement
  Direct measures of the
    Software process
      Ex., cost, effort, etc.
    Software product
      Ex., lines of code produced, execution speed, defects reported, etc.
  Indirect measures of the
    Software product
      Ex. functionality, quality, complexity, efficiency, reliability, etc.

## Slide 14: Software Measurement
Software Metrics for Software Cost and Effort Estimations.
  Size-Oriented Metrics
  Function-Oriented Metrics
  Object-Oriented Metrics
  Use-Case–Oriented Metrics

## Slide 15: 1. Size-Oriented Metrics
Derived by normalizing (standardizing) quality and/or productivity measures by considering the size of the software produced.
Thousand lines of code (KLOC) are often chosen as the normalization value.
A set of simple size-oriented metrics can be developed for each project
  Errors per KLOC (thousand lines of code)
  Defects per KLOC
  $ per KLOC
  Pages of documentation per KLOC

## Slide 16: 1. Size-Oriented Metrics (Cont…)
In addition, other interesting metrics can be computed, like
  Errors per person-month
  KLOC per person-month
  $ per page of documentation
Size-oriented metrics are not universally accepted as the best way to measure the software process.
Opponents argue that KLOC measurements
  Are dependent on the programming language
  Penalize well-designed but short programs
  Cannot easily accommodate nonprocedural languages
  Require a level of detail that may be difficult to achieve

## Slide 17: 2. Function-Oriented Metrics
Function-oriented metrics use a measure of the functionality delivered by the application as a normalization value
Most widely used metric of this type is the Function Point
  FP = Count Total * [0.65 + 0.01 * Sum (Value Adjustment Factors)]
Function Point values on past projects can be used to compute,
  for example, the average number of lines of code per function point

## Slide 18: 2. Function Point Controversy
Like the KLOC measure, function point also has proponents and opponents.
Proponents claim that
  FP is programming language independent.
  FP is based on data that are more likely to be known in the early stages of a project, making it more attractive as an estimation approach.
Opponents claim that
  FP requires some “sleight of hand” because the computation is based on subjective data.
  Counts of the information domain can be difficult to collect.
  FP has no direct physical meaning, it’s just a number.

## Slide 19: 3. Object-Oriented Metrics
Conventional software project metrics (LOC or FP) can be used to estimate object-oriented software projects.
However, these metrics do not provide enough granularity (detailing) for the schedule and effort adjustments that are required as you iterate through an evolutionary or incremental process.
Lorenz and Kidd suggest the following set of metrics for OO projects
  Number of scenario scripts
  Number of key classes (the highly independent components)
  Number of support classes

## Slide 20: 4. Use-Case–Oriented Metrics
Like FP, the use case is defined early in the software process, allowing it to be used for estimation before significant (valuable) modeling and construction activities are initiated.
Use cases describe (indirectly, at least) user-visible functions and features that are basic requirements for a system.
The use case is independent of programming language, because use cases can be created at vastly different levels of abstraction, there is no standard “size” for a use case.
Without a standard measure of what a use case is, its application as a normalization measure is suspect (doubtful).
  Ex., effort expended / use case

## Slide 21: Function Point Metrics
The function point (FP) metric can be used effectively as a means for measuring the functionality delivered by a system.
Using historical data, the FP metric can be used to
  estimate the cost or effort required to design, code, and test the software;
  predict the number of errors that will be encountered during testing; and
  forecast the number of components and/or the number of projected source lines in the implemented system.

## Slide 22: Function Point Components
Function / Application
User / Event
User / Event
Other Applications
external inquiries (EQs)
external outputs (EOs)
external inputs (EIs)
external interface files (EIFs)
internal logical files (ILFs)

## Slide 23: Function Point Components
Information domain values (components) are defined in the following manner
  Number of external inputs (EIs)
    input data originates from a user or is transmitted from another application.
  Number of external outputs (EOs)
    external output is derived data within the application that provides information to the user.
    output refers to reports, screens, error messages, etc.
  Number of external inquiries (EQs)
    external inquiry is defined as an online input that results in the generation of some immediate software response in the form of an online output.

## Slide 24: Function Point Components
  Number of internal logical files (ILFs)
    internal logical file is a logical grouping of data that resides within the application’s boundary and is maintained via external inputs.
  Number of external interface files (EIFs)
    external interface file is a logical grouping of data that resides external to the application but provides information that may be of use to the another application.

## Slide 25: Compute Function Points
Formula
  FP = Count Total * [ 0.65 + 0.01 * ∑(Fi) ]
    Count Total = Information Domain Value Count * weighting factor
    Weighting factor is determined for each organization via empirical (based on experience) data.
    Fi (i=1 to 14) are complexity value adjustment factors (VAF).

## Slide 26: Compute Function Points (Cont…)

## Slide 27: Value Adjustment Factors
F1. Data Communication
F2. Distributed Data Processing
F3. Performance
F4. Heavily Used Configuration
F5. Transaction Role
F6. Online Data Entry
F7. End-User Efficiency
F8. Online Update
F9. Complex Processing
F10. Reusability
F11. Installation Ease
F12. Operational Ease
F13. Multiple Sites
F14. Facilitate Change

## Slide 28: Function Point Example

## Slide 29: Function Point Example (Cont…)
Used Adjustment Factors and assumed values are,
  F09. Complex internal processing = 3
  F10. Code to be reusable = 2
  F03. High performance = 4
  F13. Multiple sites = 3
  F02. Distributed processing = 5
Project Adjustment Factor (VAF) = 17
Adjustment calculation
  Adjusted FP = Count Total * [ 0.65 + 0.01 * ∑(Fi) ]
    = Unadjusted FP x [ 0.65 + (0.01 x Adjustment Factor) ]
    = 50 x [ 0.65 + (0.01 x 17) ]
    = 50 x [ 0.82 ]
    = 41

## Slide 30: Compute Function Points Example-2
Study of requirement specification for a project has produced following results
  Need for 7 inputs, 10 outputs, 6 inquiries, 17 files and 4 external interfaces.
  Input and external interface function point attributes are of average complexity and all other function points attributes are of low complexity.
  Determine adjusted function points assuming complexity adjustment value is 32.
    Count Total = 233
    FP = 226.01

## Slide 31: Software Project Estimation
It can be transformed from a black art to a series of systematic steps that provide estimates with acceptable risk.
To achieve reliable cost and effort estimates, a number of options arise:
  Delay estimation until late in the project (obviously, we can achieve 100 percent accurate estimates after the project is complete!).
  Base estimates on similar projects that have already been completed.
  Use relatively simple decomposition techniques to generate project cost and effort estimates.
  Use one or more empirical models for software cost and effort estimation.

## Slide 32: Software Project Decomposing
Software project estimation is a form of problem solving and in most cases, the problem to be solved is too complex to be considered in one piece.
For this reason, decomposing the problem, re-characterizing it as a set of smaller problems is required.
Before an estimate can be made, the project planner must understand the scope of the software to be built and must generate an estimate of its “size”.

## Slide 33: Decomposition Techniques
Software Sizing
Problem based Estimation
  LOC (Lines of Code) based
  FP (Function Point) based
Process based Estimation
Estimation with Use-cases

## Slide 34: 1. Software Sizing
Putnam and Myers suggest four different approaches to the sizing problem:
  “Fuzzy logic” sizing
    This approach uses the approximate reasoning techniques that are the cornerstone of fuzzy logic.
  Function Point sizing
    The planner develops estimates of the information domain characteristics.
  Standard Component sizing
    Estimate the number of occurrences of each standard component.
    Use historical project data to determine the delivered LOC size per standard component.

## Slide 35: 1. Software Sizing (Cont…)
  Change sizing
    Used when changes are being made to existing software.
    Estimate the number and type of modifications that must be accomplished.
    An effort ratio is then used to estimate each type of change and the size of the change.

## Slide 36: 2. Problem-Based Estimation
Start with a bounded statement of scope.
Decompose the software into problem functions that can each be estimated individually.
Compute an LOC or FP value for each function.
Derive cost or effort estimates by applying the LOC or FP values to your baseline productivity metrics.
  Ex., LOC/person-month or FP/person-month
Combine function estimates to produce an overall estimate for the entire project.

## Slide 37: 2. Problem-Based Estimation (Cont…)
In general, the LOC/pm and FP/pm metrics should be computed by project domain.
  Important factors are team size, application area and complexity.
LOC and FP estimation differ in the level of detail required for decomposition with each value.
  For LOC, decomposition of functions is essential and should go into considerable detail (the more detail, the more accurate the estimate)
  For FP, decomposition occurs for the five information domain characteristics and the 14 adjustment factors.
    External Inputs, External Outputs, External Inquiries, Internal Logical Files, External Interface Files
pm = person month

## Slide 38: 2. Problem-Based Estimation (Cont…)
For both approaches, the planner uses lessons learned to estimate,
  An optimistic (Sopt), most likely (Sm), and pessimistic (Spess) estimates Size (S) value for each function or count.
  Then the expected Size value S is computed as follows:
    S = (Sopt + 4 Sm + Spess)/6
Historical LOC or FP data is then compared to S in order to cross-check it.

## Slide 39: 3. Process-Based Estimation
Process-based estimation is obtained from “process framework”
application
functions
framework activities
Effort required to accomplish
each framework activity for each application function

## Slide 40: 3. Process-Based Estimation (Cont…)
This is one of the most commonly used technique.
Identify the set of functions that the software needs to perform as obtained from the project scope.
Identify the series of framework activities that need to be performed for each function.
Estimate the effort (in person months) that will be required to accomplish each software process activity for each function.
Apply average labor rates (i.e., cost/unit effort) to the effort estimated for each process activity.
Compute the total cost and effort for each function and each framework activity.

## Slide 41: 3. Process-Based Estimation (Cont…)
Compare the resulting values to those obtained by way of the LOC and FP estimates.
  If both sets of estimates agree, then your numbers are highly reliable.
  Otherwise, conduct further investigation and analysis concerning the function and activity breakdown.

## Slide 42: 4. Estimation with Use-Cases
Developing an estimation approach with use cases is problematic for the following reasons:
  Use cases are described using many different formats and styles—there is no standard form.
  Use cases represent an external view (the user’s view) of the software and can therefore be written at many different levels of abstraction.
  Use cases do not address the complexity of the functions and features that are described.
  Use cases can describe complex behavior (Ex., interactions) that involve many functions and features.
Although a number of investigators have considered use cases as an estimation input.

## Slide 43: 4. Estimation with Use-Cases (Cont…)
Before use cases can be used for estimation,
  the level within the structural hierarchy is established,
  the average length (in pages) of each use case is determined,
  the type of software (e.g., real-time, business, engineering/scientific, WebApp, embedded) is defined, and
  a rough architecture for the system is considered.
Once these characteristics are established,
  empirical data may be used to establish the estimated number of LOC or FP per use case (for each level of the hierarchy).
Historical data are then used to compute the effort required to develop the system.

## Slide 44: Empirical Estimation Models
Source Lines of Code (SLOC)
Function Point (FP)
Constructive Cost Model (COCOMO)
Notes: Total count=233
Fp=226.01

## Slide 45: SLOC
The project size helps to determine the resources, effort, and duration of the project.
SLOC is defined as the Source Lines of Code that are delivered as part of the product.
The effort spent on creating the SLOC is expressed in relation to thousand lines of code (KLOC).
This technique includes the calculation of Lines of Code, Documentation of Pages, Inputs, Outputs, and Components of a software program.
The SLOC technique is language-dependent.
  The effort required to calculate SLOC may not be the same for all languages.
Notes: Total count=233
Fp=226.01

## Slide 46: COCOMO II
Stands for COnstructive COst MOdel.
Introduced by Barry Boehm in 1981.
It became one of the well-known and widely-used estimation models in the industry.
It has evolved into a more comprehensive (complete) estimation model called COCOMO II.
As with all estimation models, it requires sizing information,
and accepts it in three forms: object points, function points, and lines of source code.

## Slide 47: COCOMO II (Cont…)
COCOMO II is actually a hierarchy of estimation models that address the following areas:
  Application composition model
    Used during the early stages of software engineering when the following are important,
      Prototyping of user interfaces
      Consideration of software and system interaction
      Assessment of performance
      Evaluation of technology maturity
  Early design stage model
    Used once requirements have been stabilized and basic software architecture has been established
  Post-architecture stage model
    Used during the construction of the software

## Slide 48: Organic, Semidetached and Embedded software projects
Organic
  A development project can be considered of organic type,
    if the project deals with developing a well understood application program,
    the size of the development team is reasonably small, and
    the team members are experienced in developing similar types of projects.
Semidetached
  A development project can be considered of semidetached type,
    if the development consists of a mixture of experienced and inexperienced staff.
    Team members may have limited experience on related systems but may be unfamiliar with some aspects of the system being developed.

## Slide 49: Organic, Semidetached and Embedded software projects
Embedded
  A development project is considered to be of embedded type,
    if the software being developed is strongly coupled to complex hardware, or
    if the stringent regulations (strong rules) on the operational procedures exist.

## Slide 50: COCOMO II (Cont…)
The basic COCOMO model gives an approximate estimate of the project parameters.
The basic COCOMO estimation model is given by following expressions:
  Effort = a1 x (KLOC)a2 PM (person Month)
  Time of Development = b1 x (Effort)b2 Months
    Where, a1,a2,b1,b2 are constants for each category of software products
Estimation of Effort
  Organic: Effort = 2.4 (KLOC)1.05 PM
  Semi-detached: Effort = 3.0 (KLOC)1.12 PM
  Embedded: Effort = 3.6 (KLOC)1.20 PM

## Slide 51: COCOMO II (Cont…)
Estimation Time of Development
  Organic: Time of Development = 2.5 (Effort)0.38 Months
  Semi-detached: Time of Development = 2.5 (Effort)0.35 Months
  Embedded: Time of Development = 2.5 (Effort)0.32 Months

## Slide 52: Example
Assume that the size of an organic software product has been estimated to be 32,000 lines of source code.
Assume that the average salary of software be Rs. 15,000/- month.
Determine the effort required to develop the software product and the nominal development time.
  Effort= 2.4 x (32)1.05 = 91 PM
  Time of development = 2.5 x (91)0.38 = 14 months
  Cost= 14 x 15,000 = Rs. 2,10,000/-

## Slide 53: Project Scheduling & Tracking
It is an action that distributes estimated effort across the planned project duration, by allocating the effort to specific software engineering tasks.

## Slide 54: Scheduling Principles
Compartmentalization
  the product and process must be decomposed into a manageable number of activities and tasks.
Interdependency
  tasks that can be completed in parallel must be separated from those that must completed serially.
Time Allocation
  every task has start and completion dates that take the task interdependencies into account.
Effort Validation
  project manager must ensure that on any given day there are enough staff members assigned to completed the tasks within the time estimated in the project plan.

## Slide 55: Scheduling Principles (Cont…)
Defined Responsibilities
  every scheduled task needs to be assigned to a specific team member.
Defined Outcomes
  every task in the schedule needs to have a defined outcome (usually a work product or deliverable) .
Defined Milestones
  a milestone is accomplished when one or more work products from an engineering task have passed quality review.

## Slide 56: Effort Distribution
General guideline: 40-20-40 rule
  40% or more of all effort allocated to analysis and design tasks.
  20% of effort allocated to programming.
  40% of effort allocated to testing.
Characteristics of each project dictate the distribution of effort.
Although most software organizations encounter the following projects types:
  Concept Development
    initiated to explore new business concept or new application of technology.
  New Application Development
    new product requested by customer.

## Slide 57: Effort Distribution (Cont…)
  Application Enhancement
    major modifications to function, performance or interfaces (observable to user).
  Application Maintenance
    correcting, adapting or extending existing software (not immediately obvious to user).
  Reengineering
    rebuilding all (or part) of a existing (legacy) system.

## Slide 58: Scheduling Methods
It does not differ greatly from scheduling of any multitask engineering effort.
Therefore, generalized project scheduling tools and techniques can be applied with little modification for software projects.
Two project scheduling methods that can be applied to software development.
  Program Evaluation and Review Technique (PERT)
  Critical Path Method (CPM)

## Slide 59: Scheduling Methods (Cont…)
Both techniques are driven by information already developed in earlier project planning activities:
  estimates of effort
  a decomposition of the product function
  the selection of the appropriate process model and task set
  decomposition of the tasks that are selected
Both PERT and CPM provide quantitative tools that allow you to:
  Determine the critical path—the chain of tasks that determines the duration of the project.
  Establish “most likely” time estimates for individual tasks by applying statistical models.
  Calculate “boundary times” that define a “time window” for a particular task.

## Slide 60: Project Schedule Tracking
The project schedule provides a road map for a software project manager.
It defines the tasks and milestones.
Several ways to track a project schedule:
  Conducting periodic project status meeting.
  Evaluating the review results in the software process.
  Determine if formal project milestones have been accomplished.
  Compare actual start date to planned start date for each task.
  Informal meeting with practitioners.
  Using earned value analysis to assess progress quantitatively.

## Slide 61: Project Tracking (Cont…)
Project manager takes the control of the schedule in the aspects of:
  Project Staffing
  Project Problems
  Project Resources
  Reviews
  Project Budget

## Slide 62: Risk Analysis and Management
Risk Identification
Risk Projection
Risk Refinement
Risk Mitigation

## Slide 63: Definition of Risk
A risk is a potential (probable) problem – which might happen and might not.
Conceptual definition of risk.
  Risk concerns future happenings.
  Risk involves change in mind, opinion, actions, places, etc.
  Risk involves choice and the uncertainty that choice entails.
Two characteristics of risk
  Uncertainty
    the risk may or may not happen, so there are no 100% risks (some of those may called constraints).
  Loss
    the risk becomes a reality and unwanted consequences or losses occur.

## Slide 64: Risk Categorization: Approach-1
Project risks
  They threaten the project plan.
  If they become real, it is likely that the project schedule will slip and that costs will increase.
Technical risks
  They threaten the quality and timeliness of the software to be produced.
  If they become real, implementation may become difficult or impossible.
Business risks
  They threaten the feasibility of the software to be built.
  If they become real, they threaten the project or the product.

## Slide 65: Risk Categorization: Approach-1
Sub-categories of Business risks
  Market risk
    Building an excellent product or system that no one really wants.
  Strategic risk
    Building a product that no longer fits into the overall business strategy for the company.
  Sales risk
    Building a product that the sales force doesn't understand how to sell.
  Management risk
    Losing the support of senior management due to a change in focus or a change in people.
  Budget risk
    Losing budgetary or personnel commitment.

## Slide 66: Risk Categorization: Approach-2
Known risks
  Those risks that can be uncovered after careful evaluation of
    the project plan,
    the business and technical environment in which the project is being developed, and
    other reliable information sources (Ex. unrealistic delivery date)
Predictable risks
  Those risks that are deduced (draw conclusion) from past project experience (Ex. past turnover)
Unpredictable risks
  Those risks that can and do occur, but are extremely difficult to identify in advance.

## Slide 67: Reactive vs. Proactive Risk Strategies
Reactive risk strategies
  "Don't worry, I will think of something“.
  The majority of software teams and managers rely on this approach.
  Nothing is done about risks until something goes wrong.
    The team then flies into action in an attempt to correct the problem rapidly (fire fighting).
  Crisis management is the choice of management techniques.
Proactive risk strategies
  Steps for risk management are followed.
  Primary objective is to avoid risk and to have an emergency plan in place
    to handle unavoidable risks in a controlled and effective manner.

## Slide 68: Steps for Risk Management
Identify possible risks and recognize what can go wrong.
Analyze each risk to estimate the probability that it will occur and the impact (i.e., damage) that it will do if it does occur.
Rank the risks by probability and impact
  Impact may be negligible, marginal, critical, and catastrophic.
Develop a contingency plan to manage those risks having high probability and high impact.

## Slide 69: Risk Identification

## Slide 70: Risk Identification
Risk identification is a systematic attempt to specify threats to the project plan.
By identifying known and predictable risks, the project manager takes a first step toward,
  avoiding them when possible
  controlling them when necessary
Generic Risks
  Risks that are a potential threat to every software project.
Product-specific Risks
  Risks that can be identified only by clear understanding of the technology, the people and the environment, that is specific to the software that is to be built.

## Slide 71: Known and Predictable Risk Categories
One method for identifying risks is to create a risk item checklist.
The checklist can be used for risk identification which focuses on some subset of known and predictable risks in the following generic subcategories:
  Product Size
    risks associated with overall size of the software to be built.
  Business Impact
    risks associated with constraints imposed by management or the marketplace.
  Customer Characteristics
    risks associated with sophistication of the customer and the developer's ability to communicate with the customer in a timely manner.

## Slide 72: Known and Predictable Risk Categories
  Process Definition
    risks associated with the degree to which the software process has been defined and is followed.
  Development Environment
    risks associated with availability and quality of the tools to be used to build the project.
  Technology to be Built
    risks associated with complexity of the system to be built and the “newness” of the technology in the system.
  Staff Size and Experience
    risks associated with overall technical and project experience of the software engineers who will do the work.

## Slide 73: Risk Projection (Estimation)

## Slide 74: Risk Projection (Estimation)
Risk projection (or estimation) attempts to rate each risk in two ways.
  The probability that the risk is real.
  The consequence (effect) of the problems associated with the risk.
Risk Projection/Estimation Steps
  Establish a scale that reflects the perceived likelihood (probability) of a risk.
    Ex., 1-low, 10-high
  Explain the consequences of the risk.
  Estimate the impact of the risk on the project and product.
  Note the overall accuracy of the risk projection so that there will be no misunderstandings.

## Slide 75: Risk Mitigation, Monitoring, and Management

## Slide 76: Risk Mitigation, Monitoring, and Management
An effective strategy for dealing with risk must consider three issues (Note: these are not mutually exclusive)
  Risk mitigation (i.e., avoidance)
  Risk monitoring
  Risk management and contingency planning

## Slide 77: Risk Mitigation
Risk mitigation (avoidance) is the primary strategy and is achieved through a plan
For Ex., Risk of high staff turnover
  To mitigate this risk, you would develop a strategy for reducing turnover.
  The possible steps to be taken are:
    Meet with current staff to determine causes for turnover (e.g., poor working conditions, low pay, and competitive job market).
    Mitigate those causes that are under your control before the project starts.
    Once the project commences, assume turnover will occur and develop techniques to ensure continuity when people leave.
    Organize project teams so that information about each development activity is widely dispersed.

## Slide 78: Risk Mitigation
    Define work product standards and establish mechanisms to be sure that all models and documents are developed in a timely manner.
    Conduct peer reviews of all work (so that more than one person is “up to speed”).
    Assign a backup staff member for every critical technologist.

## Slide 79: The W5HH Principle for Project Management
Boehm suggests an approach (W5HH) that addresses project objectives, milestones and schedules, responsibilities, management and technical approaches, and required resources.
  Why is the system being developed?
    Enables all parties to assess the validity of business reasons for the software work.
  What will be done?
    Establish the task set that will be required.
  When will it be accomplished?
    Project schedule to achieve milestone.
  Who is responsible?
    Role and responsibility of each member.

## Slide 80: The W5HH Principle for Project Management
  Where are they organizationally located?
    Customer, end user and other stakeholders also have responsibility.
  How will the job be done technically and managerially?
    Management and technical strategy must be defined.
  How much of each resource is needed?
    Develop estimation.
It is applicable regardless of size or complexity of software project.

## Slide 81: Summary
Process, Project and Product Metrics
Software Measurement
Software Project Estimation
Software Project Decomposing
Empirical Estimation Models
Project Scheduling & Tracking
Risk Analysis and Management
W5HH Principle for Project Management